## 프로젝트 간트차트
|  | WELCOME TO THE HOUSE 전체 프로젝트 진행도 | [8 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com.
|  |  | 프로젝트 시작 | 2018-04-09 |  |  |  | Display Week | 3 |  | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7
|  |  | 프로젝트 담당 PD | 지현우 | [6 empty] | 2018-04-23 | [6 empty] | 2018-04-30 | [6 empty] | 2018-05-07 | [6 empty] | 2018-05-14 | [6 empty] | 2018-05-21
[11 empty] | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29 | 2018-04-30 | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-05 | 2018-05-06 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-12 | 2018-05-13 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2018-05-20 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2018-05-27
주요일정 |  | WBS | 업무 | 담당자 | PREDECESSOR | 시작일 | 마감일 | 기간 | 공정률(%) | WORK DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
|  | 1 | [프로토타입 대비 주요 기획 및 시스템 구현] |  |  |  | - |  |  | -
| 컨텐츠 | 1.1 | 컨텐츠 기획서 초안 작성 | 차정현 |  | 2018-04-09 | 2018-04-15 | 7 | 100% | 5
| 시스템 | 1.2 | 시스템 기획서 초안 작성 | 우정윤,허지훈 |  | 2018-04-09 | 2018-04-15 | 7 | 100% | 5
|  | 1.3 | 필수 시스템 구현 | 우정윤,허지훈 |  | 2018-04-19 | 2018-04-26 | 8 | 100% | 6
|  | 1.3.1 | 가스 게이지 초기 작업 | 우정윤 |  | 2018-04-19 | 2018-04-20 | 2 | 100% | 2
|  | 1.3.2 | 인벤토리 시스템 초기 작업 | 허지훈 |  | 2018-04-19 | 2018-04-27 | 9 | 100% | 9
|  | 1.3.3 | 게임 시작, 종료 화면 작업 | 우정윤 |  | 2018-04-20 | 2018-04-20 | 1 | 100% | 1
프로토타입 |  | 1.3.4 | 시선 마우스 시스템 초기 작업 | 우정윤 |  | 2018-04-19 | 2018-04-19 | 1 | 100% | 5
|  | 1.3.5 | 1챕터 맵 초안 작업 | 차정현 |  | 2018-04-23 | 2018-05-01 | 9 | 100% | 5
|  | 1.3.6 | 플래쉬 라이트 추가 | 우정윤 |  | 2018-04-23 | 2018-05-01 | 9 | 100% | 5
|  | 1.3.7 | 앰비언트 라이트 추가 | 우정윤 |  | 2018-04-23 | 2018-04-26 | 4 | 100% | 4
|  | 1.4 | QA 체크리스트 및 TC 초안 작성 | 이병관 |  | 2018-04-12 | 2018-04-15 | 4 | 100% | 2
|  | 1.5 | 애니메이션 제작 | 이병관 |  | 2018-04-16 | 2018-04-16 | 1 | 100% | 1
|  | 1.5.1 | 테스트용 애니메이션 추가 | 우정윤 |  | 2018-04-25 | 2018-04-29 | 5 | 100% | 3
마일스톤 |  | 1.6 | 빌드 | 우정윤 |  | 2018-05-02 | 2018-05-02 | 1 | 100% | 1
|  | 2 | [CBT 대비 주요 기획 및 시스템 구현] |  |  |  | - |  |  | -
|  | 2.1 | 1챕터 컨텐츠 기획서 퍼즐 수정 및 보완 | 이병관 |  | 2018-05-03 | 2018-05-07 | 5 | 100% | 3
|  | 2.2 | 1챕터 시스템 기획서 수정 및 보완 | 우정윤, 허지훈 |  | 2018-05-03 | 2018-05-07 | 5 | 100% | 3
|  | 2.2.1 | 데이터 테이블 초안 작성 | 우정윤 |  | 2018-05-08 | 2018-05-08 | 1 | 100% | 1
|  | 2.3 | 1챕터 맵 완성 | 차정현 |  | 2018-05-03 | 2018-05-08 | 6 | 90% | 4
|  | 2.4 | 1챕터 인벤토리 오브젝트 상호작용 | 허지훈 |  | 2018-05-08 | 2018-05-10 | 3 | 90% | 3
CBT 대비 |  | 2.5 | 1챕터 키패드 시스템 구현 | 우정윤 |  | 2018-02-17 | 2018-02-22 | 6 | 100% | 4
|  | 2.6 | 1챕터 오브젝트 애니메이션 | 우정윤 |  | 2018-04-30 | 2018-05-02 | 3 | 95% | 3
|  | 2.7 | 1챕터 맵 수정 | 차정현 |  | 2018-05-01 | 2018-05-05 | 5 | 98% | 4
|  | 2.8 | 배관 가스 파티클 구현 | 우정윤 |  | 2018-05-03 | 2018-05-06 17:36 | 4.7333 | 100% | 2
|  | 2.9 | 가스 파티클 구현 | 허지훈 |  | 2018-05-03 | 2018-05-06 20:21 | 4.8476 | 100% | 2
|  | 2.10 | 1챕터 오브젝트 수정 | 임주영 |  | 2018-05-10 | 2018-05-11 | 2 | 100% | 2
|  | 2.10.1 | CBT 대비 QA 체크리스트 작성 | 차정현 |  | 2018-05-17 | 2018-05-21 01:50 | 5.0762 | 0% | 3
|  | 2.11 | CBT 대비 TC 작성 | 차정현 |  | 2018-04-30 | 2018-05-04 04:34 | 5.1905 | 0% | 5
마일스톤 |  | 2.12 | 빌드 | 우정윤 |  | 2018-05-10 | 2018-05-10 | 1 | 100% | 1
|  | 2.13 | 튜토리얼 용 에셋 탐색 | 허지훈 |  | 2018-05-11 | 2018-05-14 | 4 | 100% | 2
|  | 2.14 | 튜토리얼 맵 제작 | 허지훈,차정현 |  | 2018-05-12 | 2018-05-16 | 5 | 200% | 3
|  | 2.15 | 튜토리얼 제작 | 우정윤 |  | 2018-05-11 | 2018-05-14 | 4 | 100% | 2
|  | 2.16 |  |  |  | 2018-05-08 | 2018-05-12 15:33 | 5.6476 | 0% | 4
|  | 2.17 |  |  |  | 2018-02-17 | 2018-02-21 18:17 | 5.7619 | 0% | 3
|  | 2.18 |  |  |  | 2018-04-30 | 2018-05-04 21:02 | 5.8762 | 0% | 5
|  | 2.19 |  |  |  | 2018-05-01 | 2018-05-05 23:46 | 5.9905 | 0% | 4
|  | 3 | [Task Category] |  |  |  | - |  |  | -
|  | 3.1 | [Task] |  |  | 2018-02-10 | 2018-02-13 | 4 | 0% | 2
4
|  | 4.1 | [Task] |  |  | 2018-02-14 | 2018-02-16 | 3 | 0% | 3
|  | 4.2 | [Task] |  |  | 2018-02-14 | 2018-02-16 | 3 | 0% | 3
|  | 4.3 | [Task] |  |  | 2018-02-17 | 2018-02-22 | 6 | 0% | 4
|  | 4.4 | [Task] |  |  | 2018-02-23 | 2018-02-25 | 3 | 0% | 1
|  | 5 | [Task Category] |  |  |  | - |  |  | -
|  | 5.1 | [Task] |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
|  | 5.2 | [Task] |  |  | 2018-01-30 | 2018-01-30 | 1 | 0% | 1
|  | 5.3 | [Task] |  |  | 2018-01-31 | 2018-01-31 | 1 | 0% | 1
|  | 5.4 | [Task] |  |  | 2018-02-01 | 2018-02-01 | 1 | 0% | 1
|  | 5.5 | [Task] |  |  | 2018-02-02 | 2018-02-02 | 1 | 0% | 1
-
-
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
|  | 1 | [ Level 1 Task or Phase ] |  |  |  | - |  |  | -
|  | 1.1 | . [ Level 2 Task ] |  |  |  | - |  |  | -
|  | 1.1.1 | . . [ Level 3 Task ] |  |  |  | - |  |  | -
|  | 1.1.1.1 | . . . [ Level 4 Task ] |  |  |  | - |  |  | -
기준 공정률
[7 empty] | 프로토타입 | 20
[7 empty] | CBT 마일스톤 | 10
[7 empty] | CBT | 15
[7 empty] | OBT 마일스톤 | 20
[7 empty] | OBT 까지 | 25
[7 empty] | 릴리즈 준비기간 | 10
[7 empty] | 총 기준 공정 | 100
Note on C7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on D7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on E7: Task Lead Enter the name of the Task Lead in this column.
Note on F7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on G7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on H7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on I7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on J7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on K7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.

## 공정률
이름 | 업무 |  |  | 공정률
[6 empty] | 5월 14일 |  |  | 5월 15일 |  |  | 5월 16일 |  |  | 5월 17일 |  |  | 5월 18일 |  |  | 5월 19일 |  |  | 3월 20일 |  |  | 3월 21일 |  |  | 5월 22일 |  |  | 5월 23일 |  |  | 5월 24일 |  |  | 5월 25일 |  |  | 3월 26일 |  |  | 3월 27일 |  |  | 3월 28일 |  |  | 3월 29일 |  |  | 3월 30일 |  |  | 3월 31일 |  |  | 4월 1일 |  |  | 4월 2일
| 대분류 | 중분류 | 소분류 | 5월 12일 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률 | 목표 | 완료 | 공정률
우정윤 | 기획 | 시스템 기획서 작성 | 필요 시스템 작성 |  |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 수정 | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100%
| 시스템 | 튜토리얼 구현 | 구현 스크립트 짜기 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 맵 배치 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 플레이어 추가 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 혈흔 이동 오브젝트 추가 |  |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 플래쉬 라이트 추가 |  |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 튜토리얼 후 씬 전환 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 튜토리얼 구동 최적화 작업 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 빌드 | - | 0% | o | - | 62.5% | o | - | 87.5% | o | - | 87.5% | o | - | 87.5% | o | - | 87.5% | o | - | 87.5% | o | - | 83.33% | o | - | 83.33% | o | - | 83.33% | o | - | 83.33% | o | - | 83.33% | o | - | 83.33% | o | - | 83.33% | o | - | 83.33% | o | - | 83.33% | o | - | 83.33% | o | - | 83.33% | o | - | 83.33% | o | - | 83.33% | o | - | 83.33%
|  | 튜토리얼 복구 | 작업한 내용 복구 | - |  | - | - | 0% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  | 1번방 구현 | 1번방 서랍장 키패드 배치 | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 서랍장 키패드 구현 | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 캐비닛 키패드 배치 | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 캐비닛 키패드 구현 | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 의자 움직임 이벤트 구현 | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 액자 떨어짐 이벤트 구현 | - |  | - | - |  | - | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 빌드 | - | 0% | - | - | 0% | - | - | 40% | - | - | 40% | - | - | 40% | - | - | 33.33% | - | - | 33.33% | - | - | 33.33% | - | - | 53.33% | - | - | 53.33% | - | - | 53.33% | - | - | 53.33% | - | - | 80% | - | - | 93.33% | - | - | 93.33% | - | - | 93.33% | - | - | 93.33% | - | - | 93.33% | - | - | 93.33% | - | - | 93.33% | - | - | 93.33%
|  | 2번방 구현 | 2번방 캐비닛 키패드 구현 | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 16.67% | - | - | 16.67% | - | - | 16.67% | - | - | 16.67% | - | - | 16.67% | - | - | 16.67% | o | o | 33.33% | o | o | 33.33% | o | o | 33.33% | o | o | 33.33% | o | o | 33.33% | o | o | 33.33% | o | o | 33.33% | o | o | 33.33%
|  | 필요 시스템 |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 8.333% | - | - | 25% | o | o | 41.67% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75%
|  | 기타 시스템 |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 50% | - | - | 58.33% | - | - | 58.33% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100%
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 16.67% | - | - | 25% | - | - | 25% | o | o | 33.33% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75% | o | o | 75%
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 25% | - | - | 33.33% | - | - | 33.33% | o | - | 75% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100%
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0%
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 10% | - | - | 10% | - | - | 10% | - | - | 10% | - | - | 10% | - | - | 10% | - | - | 10% | o | - | 40% | o | - | 40% | o | o | 90% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100%
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0%
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | - |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o |  | - | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 25% | - | - | 25% | - | - | 25% | - | - | 25% | - | - | 50% | - | - | 50% | - | - | 50% | - | - | 50% | - | - | 50% | - | - | 60% | - | - | 75% | - | - | 75% | o | - | 75% | o | o | 100% | o | o | 100% | o | o | 100%
허지훈 | 기획 |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 33.33% | o | o | 53.33% | o | o | 53.33% | o | o | 53.33% | o | o | 53.33% | o | o | 53.33% | o | o | 53.33% | o | o | 53.33% | o | o | 53.33% | o | o | 53.33% | o | o | 53.33% | o | o | 53.33% | o | o | 53.33% | o | o | 53.33% | o | o | 53.33%
| 시스템 | 튜토리얼 구현 | 에셋 찾기 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 맵 배치 |  |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 스카이 박스 추가 | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 인벤토리 열기 | - |  | - | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 손전등 스크립트 추가 | - | 0% | - | - | 40% | o | - | 40% | o | - | 40% | o | - | 40% | o | - | 25% | o | - | 25% | o | - | 25% | o | - | 50% | o | - | 50% | o | - | 50% | o | - | 50% | o | - | 50% | o | - | 75% | o | - | 75% | o | - | 75% | o | - | 75% | o | - | 75% | o | o | 100% | o | o | 100% | o | o | 100%
|  | 인벤토리 구현 | 1번방 서랍장 키 획득 | - |  | - | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 서랍장 키 사용 | - |  | - | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 캐비닛 키 획득 | - |  | - | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 캐비닛 키 사용 | - | 0% | - | - | 0% | o | - | 0% | o | - | 0% | o | - | 0% | o | - | 0% | o | - | 25% | o | - | 25% | o | - | 25% | o | - | 25% | o | - | 50% | o | - | 50% | o | - | 50% | o | - | 50% | o | - | 50% | o | - | 50% | o | - | 75% | o | - | 75% | o | o | 100% | o | o | 100% | o | o | 100%
|  |  | 2번방 염산 획득 | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 2번방 염산 사용 | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 2번방 | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 25% | - | - | 25% | - | - | 25% | - | - | 50% | - | - | 40% | - | - | 40% | - | - | 40% | - | - | 40% | - | - | 60% | - | - | 60% | - | - | 60% | - | - | 80% | - | o | 100% | - | o | 100% | - | o | 100%
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 25% | - | - | 25% | - | - | 25% | - | - | 25% | - | - | 50% | - | - | 50% | - | - | 50% | - | - | 50% | - | - | 50% | - | - | 50% | - | - | 75% | - | - | 75% | - | o | 100% | - | o | 100% | - | o | 100%
차정현 | 맵디자인 | 1번방 맵 | 맵 초안 제작 |  |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 책상 배치 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 옷장배치 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 촛불 배치 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 캐비닛 배치 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 서랍장 배치 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 의자 배치 |  |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 시체 3개 배치 |  |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 시계 퀴즈 배치 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 열쇠 2개 배치 |  |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 글씨 퀴즈 배치 | - | 0% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100%
|  | 2번방 맵 | 맵 초안 제작 | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 간이감옥 배치 | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 천장 문 배치 |  |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 천장 위 시체 배치 |  |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 수조 배치 |  |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 염산 에셋 찾기 |  |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 염산 배치 |  |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 고깃 덩어리 배치 |  |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 탈출 열쇠 배치 | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 이벤트용 시체 배치 |  |  | - | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | o
|  |  | 천장에 달린 사람머리 배치 | - |  | - | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 슬렌더맨 배치 | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 간이감옥 퍼즐용 시체 배치 4구 배치 | - | 0% | - | - | 0% | o | o | 84.62% | o | o | 84.62% | o | o | 84.62% | o | o | 84.62% | o | o | 84.62% | o | o | 84.62% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100%
|  | 리뉴얼 맵 |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 60% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100%
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | o | - | 0% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100%
|  | 체크리스트 | CBT용 체크리스트 초안 작성 | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  | CBT용 체크리스트 완성 | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
| QA |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 8.333% | o | - | 16.67% | o | o | 25% | o | o | 41.67% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33%
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 8.333% | - | - | 13.89% | o | o | 30.56% | o | o | 41.67% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33% | o | o | 58.33%
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 2.778% | - | - | 11.11% | - | - | 11.11% | o | o | 27.78% | o | o | 44.44% | o | o | 61.11% | o | o | 61.11% | o | o | 61.11% | o | o | 61.11% | o | o | 61.11% | o | o | 61.11% | o | o | 61.11% | o | o | 61.11% | o | o | 61.11% | o | o | 61.11% | o | o | 61.11%
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100%
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | - | - | 0% | o | - | 75% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100% | o | o | 100%
이병관 | 컨텐츠 | 기획 | 연출에 필요한 에셋 탐색 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 오브젝트 리스트 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 오브젝트 배치도 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 퀴즈 기획1 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 퀴즈 기획2 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 이벤트 기획 |  |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 2번방 오브젝트 리스트 |  |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 2번방 오브젝트 배치도 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 2번방 퀴즈 기획1 | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 2번방 이벤트 기획 |  |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 통로 이벤트 기획 |  |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 2번방 오브젝트 기획 |  |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 1번방 혈흔 이동포인트 기획 |  |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 2번방 혈흔 이동포인트 기획 |  |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 통로 혈흔 이동포인트 기획 |  |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 레벨 디자인 기획 |  |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
[6 empty] | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | -
|  | 애니메이션 | 1번방 의자 움직임 애니메이션 구현 |  |  | - | - |  | o | o
|  |  | 1번방 액자 떨어짐 애니메이션 구현 |  |  | - | - |  | o | o
|  |  | 1번방 옷장 문열림 애니메이션 구현 |  |  | - | - |  | o | o
|  |  | 1번방 옷장 안 시체 ragdoll 만들기 |  |  | - | - |  | o | o
|  |  | 1번방 문 닫힘 애니메이션 |  |  | - | - |  | o | o
|  |  | 1번방 문 열림 애니메이션 |  |  | - | - |  | o | o
|  |  | 1번방 촛불 껐다 켜짐 애니메이션 구현 |  |  | - | - |  | - | -
|  |  | 1번방 서랍장 문 열림 애니메이션 구현 |  |  | - | - |  | o | o
|  |  | 1번방 캐비닛 문 열림 애니메이션 구현 |  |  | - | - |  | o | -
|  |  | 2번방 이벤트 시체 애니메이션 구현 |  |  | - | - |  | - | -
|  |  | 2번방 천장 문 애니메이션 구현 |  |  | - | - |  | - | -
|  |  | 2번방 천장 위 시체 애니메이션 구현 |  |  | - | - |  | - | -
|  |  | 2번방 캐비닛 문열림 애니메이션 구현 |  |  | - | - |  | o | o |  | o | o
|  |  | 2번방 문 열림 애니메이션 |  |  | - | - |  | - | - |  | o | o
|  |  | 통로 옷장 문 열림 애니메이션 구현 |  |  | - | - |  | - | -
|  |  | 통로 옷장 시체 애니메이션 구현 | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  | 2번방 퀴즈 기획2 | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | o |  | - | o |  | - | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | -
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | - | - |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o |  | o | o
|  |  |  | - | 0% | - | - | 20% | - | - | 46% | - | - | 45.95% | - | - | 42.86% | - | - | 46.88% | - | - | 43.33% | - | - | 43.33% | - | - | 43.33% | - | - | 43.33% | - | - | 60% | - | - | 60% | - | - | 60% | - | - | 54.55% | - | - | 68.18% | - | - | 81.82% | - | - | 81.82% | o | o | 90.91% | o | o | 100% | o | o | 100% | o | o | 100%
|  |  |  | 0% |  | 8.47% | 7.65% | 90.32% | 19.13% | 16.39% | 76.19% | 18.13% | 15.3% | -63.1% | 17.66% | 14.81% | -20.4% | 20.81% | 16.47% | 27.68% | 22.58% | 21.11% | 75.99% | 26.25% | 23.89% | 54.08% | 33.33% | 30.97% | 75% | 43.07% | 41.57% | 87.55% | 51.51% | 50.6% | 90.91% | 52.11% | 51.2% | 40% | 62.35% | 59.04% | 70.27% | 66.05% | 63.89% | 69.19% | 67.28% | 65.74% | 54.55% | 72.84% | 71.91% | 86.96% | 73.46% | 73.77% | 120% | 76.23% | 74.69% | 37.5% | 76.23% | 78.4% | 240% | 76.23% | 78.4% | 0% | 76.23% | 78.4% | 0%
[8 empty] | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률 |  |  | 당일 공정률
[7 empty] | 3.45미달 | 원인: 깃허브 오류
12.6%
|  | 공정률= 한거 셀이름 / 목표 셀이름 | [8 empty] | 6.526%
[7 empty] | 애니메이션 |  |  |  | 9.868%
|  | 당일 공정률=오늘한거-어제한거/오늘목표-어제한거 |  |  |  |  | 차정현 작업 미뤄짐 (아파서) |  |  |  | 31.8%
41.67%
튜토리얼 빌드
1번방 구현시작
애니메이션 구현 시작
2번방 배치

## 일일간트차트
|  | WELCOME TO THE HOUSE 전체 프로젝트 진행도 | [8 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com.
|  |  | 프로젝트 시작 | 2018-04-09 |  |  |  | Display Week | 3 |  | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7
|  |  | 프로젝트 담당 PD | 지현우 | [6 empty] | 2018-04-23 | [6 empty] | 2018-04-30 | [6 empty] | 2018-05-07 | [6 empty] | 2018-05-14 | [6 empty] | 2018-05-21
[11 empty] | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29 | 2018-04-30 | 2018-05-01 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-05 | 2018-05-06 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-10 | 2018-05-11 | 2018-05-12 | 2018-05-13 | 2018-05-14 | 2018-05-15 | 2018-05-16 | 2018-05-17 | 2018-05-18 | 2018-05-19 | 2018-05-20 | 2018-05-21 | 2018-05-22 | 2018-05-23 | 2018-05-24 | 2018-05-25 | 2018-05-26 | 2018-05-27
주요일정 |  | WBS | 업무 | 담당자 | PREDECESSOR | 시작일 | 마감일 | 기간 | 공정률(%) | WORK DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
|  | 1 | [프로토타입 대비 주요 기획 및 시스템 구현] |  |  |  | - |  |  | -
| 컨텐츠 | 1.1 | 컨텐츠 기획서 초안 작성 | 차정현 |  | 2018-04-09 | 2018-04-15 | 7 | 100% | 5
| 시스템 | 1.2 | 시스템 기획서 초안 작성 | 우정윤,허지훈 |  | 2018-04-09 | 2018-04-15 | 7 | 100% | 5
|  | 1.3 | 필수 시스템 구현 | 우정윤,허지훈 |  | 2018-04-19 | 2018-04-26 | 8 | 100% | 6
|  | 1.3.1 | 가스 게이지 초기 작업 | 우정윤 |  | 2018-04-19 | 2018-04-20 | 2 | 100% | 2
|  | 1.3.2 | 인벤토리 시스템 초기 작업 | 허지훈 |  | 2018-04-19 | 2018-04-27 | 9 | 100% | 9
|  | 1.3.3 | 게임 시작, 종료 화면 작업 | 우정윤 |  | 2018-04-20 | 2018-04-20 | 1 | 100% | 1
프로토타입 |  | 1.3.4 | 시선 마우스 시스템 초기 작업 | 우정윤 |  | 2018-04-19 | 2018-04-19 | 1 | 100% | 5
|  | 1.3.5 | 1챕터 맵 초안 작업 | 차정현 |  | 2018-04-23 | 2018-05-01 | 9 | 100% | 5
|  | 1.3.6 | 플래쉬 라이트 추가 | 우정윤 |  | 2018-04-23 | 2018-05-01 | 9 | 100% | 5
|  | 1.3.7 | 앰비언트 라이트 추가 | 우정윤 |  | 2018-04-23 | 2018-04-26 | 4 | 100% | 4
|  | 1.4 | QA 체크리스트 및 TC 초안 작성 | 이병관 |  | 2018-04-12 | 2018-04-15 | 4 | 100% | 2
|  | 1.5 | 애니메이션 제작 | 이병관 |  | 2018-04-16 | 2018-04-16 | 1 | 100% | 1
|  | 1.5.1 | 테스트용 애니메이션 추가 | 우정윤 |  | 2018-04-25 | 2018-04-29 | 5 | 100% | 3
마일스톤 |  | 1.6 | 빌드 | 우정윤 |  | 2018-05-02 | 2018-05-02 | 1 | 100% | 1
|  | 2 | [CBT 대비 주요 기획 및 시스템 구현] |  |  |  | - |  |  | -
|  | 2.1 | 1챕터 컨텐츠 기획서 퍼즐 수정 및 보완 | 이병관 |  | 2018-05-03 | 2018-05-07 | 5 | 100% | 3
|  | 2.2 | 1챕터 시스템 기획서 수정 및 보완 | 우정윤, 허지훈 |  | 2018-05-03 | 2018-05-07 | 5 | 100% | 3
|  | 2.2.1 | 데이터 테이블 초안 작성 | 우정윤 |  | 2018-05-08 | 2018-05-08 | 1 | 100% | 1
|  | 2.3 | 1챕터 맵 완성 | 차정현 |  | 2018-05-03 | 2018-05-08 | 6 | 90% | 4
|  | 2.4 | 1챕터 인벤토리 오브젝트 상호작용 | 허지훈 |  | 2018-05-08 | 2018-05-10 | 3 | 90% | 3
CBT 대비 |  | 2.5 | 1챕터 키패드 시스템 구현 | 우정윤 |  | 2018-02-17 | 2018-02-22 | 6 | 100% | 4
|  | 2.6 | 1챕터 오브젝트 애니메이션 | 우정윤 |  | 2018-04-30 | 2018-05-02 | 3 | 95% | 3
|  | 2.7 | 1챕터 맵 수정 | 차정현 |  | 2018-05-01 | 2018-05-05 | 5 | 98% | 4
|  | 2.8 | 배관 가스 파티클 구현 | 우정윤 |  | 2018-05-03 | 2018-05-06 17:36 | 4.7333 | 100% | 2
|  | 2.9 | 가스 파티클 구현 | 허지훈 |  | 2018-05-03 | 2018-05-06 20:21 | 4.8476 | 100% | 2
|  | 2.10 | 1챕터 오브젝트 수정 | 임주영 |  | 2018-05-10 | 2018-05-11 | 2 | 100% | 2
|  | 2.10.1 | CBT 대비 QA 체크리스트 작성 | 차정현 |  | 2018-05-17 | 2018-05-21 01:50 | 5.0762 | 0% | 3
|  | 2.11 | CBT 대비 TC 작성 | 차정현 |  | 2018-04-30 | 2018-05-04 04:34 | 5.1905 | 0% | 5
마일스톤 |  | 2.12 | 빌드 | 우정윤 |  | 2018-05-10 | 2018-05-10 | 1 | 100% | 1
|  | 2.13 | 튜토리얼 용 에셋 탐색 | 허지훈 |  | 2018-05-11 | 2018-05-14 | 4 | 100% | 2
|  | 2.14 | 튜토리얼 맵 제작 | 허지훈,차정현 |  | 2018-05-12 | 2018-05-16 | 5 | 200% | 3
|  | 2.15 | 튜토리얼 제작 | 우정윤 |  | 2018-05-11 | 2018-05-14 | 4 | 100% | 2
|  | 2.16 |  |  |  | 2018-05-08 | 2018-05-12 15:33 | 5.6476 | 0% | 4
|  | 2.17 |  |  |  | 2018-02-17 | 2018-02-21 18:17 | 5.7619 | 0% | 3
|  | 2.18 |  |  |  | 2018-04-30 | 2018-05-04 21:02 | 5.8762 | 0% | 5
|  | 2.19 |  |  |  | 2018-05-01 | 2018-05-05 23:46 | 5.9905 | 0% | 4
|  | 3 | [Task Category] |  |  |  | - |  |  | -
|  | 3.1 | [Task] |  |  | 2018-02-10 | 2018-02-13 | 4 | 0% | 2
4
|  | 4.1 | [Task] |  |  | 2018-02-14 | 2018-02-16 | 3 | 0% | 3
|  | 4.2 | [Task] |  |  | 2018-02-14 | 2018-02-16 | 3 | 0% | 3
|  | 4.3 | [Task] |  |  | 2018-02-17 | 2018-02-22 | 6 | 0% | 4
|  | 4.4 | [Task] |  |  | 2018-02-23 | 2018-02-25 | 3 | 0% | 1
|  | 5 | [Task Category] |  |  |  | - |  |  | -
|  | 5.1 | [Task] |  |  | 2018-01-29 | 2018-01-29 | 1 | 0% | 1
|  | 5.2 | [Task] |  |  | 2018-01-30 | 2018-01-30 | 1 | 0% | 1
|  | 5.3 | [Task] |  |  | 2018-01-31 | 2018-01-31 | 1 | 0% | 1
|  | 5.4 | [Task] |  |  | 2018-02-01 | 2018-02-01 | 1 | 0% | 1
|  | 5.5 | [Task] |  |  | 2018-02-02 | 2018-02-02 | 1 | 0% | 1
-
-
TEMPLATE ROWS
See the Help worksheet to learn how to use these rows. You can hide these rows before printing.
|  | 1 | [ Level 1 Task or Phase ] |  |  |  | - |  |  | -
|  | 1.1 | . [ Level 2 Task ] |  |  |  | - |  |  | -
|  | 1.1.1 | . . [ Level 3 Task ] |  |  |  | - |  |  | -
|  | 1.1.1.1 | . . . [ Level 4 Task ] |  |  |  | - |  |  | -
기준 공정률
[7 empty] | 프로토타입 | 20
[7 empty] | CBT 마일스톤 | 10
[7 empty] | CBT | 15
[7 empty] | OBT 마일스톤 | 20
[7 empty] | OBT 까지 | 25
[7 empty] | 릴리즈 준비기간 | 10
[7 empty] | 총 기준 공정 | 100
Note on C7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on D7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on E7: Task Lead Enter the name of the Task Lead in this column.
Note on F7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on G7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on H7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on I7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on J7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on K7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.